This document represents the “backward design” – all the things which need to be implemented to accomplish the chief goal listed below. Blue = the big rocks, the hard things to do; Yellow = the medium-sized things to accomplish; Green = the easy, almost immediate, things to accomplish.

Recommendation: Place all these items, whether colored or not, on a calendar and determine an “owner” for each.

Chief goal:
		Develop a BH team to engage and represent BHIVE to the community

Due date: September 1st, 2020

- Prepare and conduct a “shark tank” presentation of BHIVE to PHC.

- Determine the size of the team.

- Investigate joining the PHC.

- Determine the communication point person.

- Name the team coordinator.

- Identify from the County government to join.

- Define the roles of team members.

- Write Positioning Narrative.

- Contact Elizabeth to determine school district reps.

- Contact Aspen Point to determine who will join.

- Contact Tessa

- Put Amber on the team.

- Establish dates and times for BHIVE meetings.

- Seek to have a City Council member.

- Contact the various wards to identify a representative.

- Identify and ask a citizen representative.

- Find a business community representative.

- Engage churches for clergy support.

- Identify volunteers who might want to engage.

- Identify someone from the school board.

- Identify the strengths of the individuals who might join.

- Identify individuals who have/had BH needs (empathy).

- Identify a representative from the MSPD to be on the team.

- Ensure the diversity on the team.

- Consider a leadership/board subgroup of the team.